# DAISY Music Braille Project - Save the Date, and other news

By email: 21 January 2019

From: Sarah Morley Wilkins, Project Manager, DAISY Music Braille Project

Dear colleagues, Happy New Year!

A few updates from the project, and a great offer from Dedicon for other agencies :)

## 1. Geneva Meeting

### 1.1) Save the date and first information:

* The next DAISY Music Braille meeting will be held in Geneva on the afternoon of Tuesday 28 and all-day Wednesday 29 May 2019.
* WIPO is very kindly hosting the meeting at their headquarters.
* We will let you know exact meeting details, hotel arrangements, and online access (if available), as soon as we can.

### 1.2) Agenda:

The agenda will be more focussed than our previous Round Table meetings, focussing on:

* Requirements document for future tools, hopefully also with responses from developers;
* Guidance and specification for checking and marking up a MusicXML file to get good conversions;
* Development costs, and agencies to consider contributing to agreed plans.
* We will ask for, and circulate, updates on other work before the meeting.

## 2: News on Progress

Since our October meeting we have made good progress on our agreed objectives. We welcomed Haipeng Hu as a consultant to the project team, and with various contributions from across the project we can report a number of achievements:

### 2.1) Guidance for marking up MusicXML files to get better braille through conversion tools:

* Guidance for sighted people checking and correcting MusicXML scores has been drafted and edited.
* A MusicXML specification handbook has been drafted and annotated highlighting specific braille-music issues.
* A template has been prepared ready to populate with these two documents to create a single Handbook.
* Documents to be circulated for comment shortly.

### 2.2) Immediate fixes needed in conversion tools:

* After intensive testing (by the UK team) the three main tools have been sent issue lists: GoodFeel, Hodder and BrailleMuse.
* Some are already implementing some fixes.
* Some common big issues will be carried forward into the Requirements document

### 2.3) Requirements document:

* A requirements document, capturing the high-level needs noted so far has been drafted and edited.
* Will be circulated shortly for comment and prioritisation by agencies, educators and transcribers.

### 2.4) MusicXML/MNX improvements:

* Sibelius: bug report for MusicXML Export has been sent to beta test group.
* MuseScore: bug report for MusicXML export submitted to forum.
* MNX Community Group: sent them info for their end-January meeting, expressing our intention to contribute to MNX specification and testing.
* SMuFL: Mapping is underway of the Standard Music Font Layout Glyphs to braille symbols.

### 2.5) Hodder trial at Dedicon:

* After an intensive trial in the autumn, Dedicon reports very positive feedback, getting excellent performance for almost all score types.
* Final report to be circulated soon.
* GREAT OFFER: Dedicon is now open to taking music braille transcription orders for other agencies. Please contact their Director of Production – EdwinMeijerink [at] dedicon [dot] nl

We look forward to continuing to work with you during 2019 to secure the longer-term future for music braille for our next generations. Thank you in advance for your collaboration efforts. It really does make a difference.

With best regards,
Arne and Sarah

---
Dr. Sarah Morley Wilkins,

Project Manager, DAISY Music Braille Collaboration
sarah [at] sarahmorleywilkins [dot] com

[www.daisy.org/project/daisy-music-braille](http://www.daisy.org/project/daisy-music-braille)

---

You are receiving this email because you asked to be kept informed about the DAISY Music Braille Project. If you’d like to be removed, or wish to add someone, please email us at musicbraille [at] daisy [dot] org